## Project Tracking
PROJECT TRACKING | [5 empty] | STATUS KEY | PRIORITY KEY
[6 empty] | On Hold | Low
PROJECT TITLE |  | TDM sentiment |  |  |  | Not Yet Started | Medium
Objective |  | Analyze economic articles from major U.S. newspapers (Los Angeles Times, The Washington Post, USA Today, Chicago Tribune, and The New York Times) using text mining and sentiment analysis. |  |  |  | In Progress | High
Complete
PROJECT DETAILS
STATUS | PRIORITY | START DATE | END DATE | TASK NAME | DESCRIPTION
Data Collection & Preprocessing |  |  |  |  | Cleaned and formatted dataset of news articles with metadata.
Complete | High | 2024-09-08 | 2024-09-08 | Data Harvest | Access and extract article data from TDM Studio for the specified newspapers.
Complete | High | 2024-09-08 | 2024-09-08 | Clean Sweep | remove duplicates, correct encoding issues, and clean text.
Complete | High | 2024-09-08 | 2024-09-08 | Metadata Mapping | mapping repository of metadata into: article titles, publication dates, word counts, sections and more.
Not Yet Started | Low |  |  | write methodology
Identify Economic Articles |  |  |  |  | Labeled dataset where each article is flagged as economic or not.
Complete | High | 2024-09-14 | 2024-09-14 | Section Sorter | Filter articles labeled as 'economy', and section counter to such as 'lifstyle' based on section metadata
Complete | High | 2024-09-14 | 2024-09-14 | Economic Classify | Implementing a logistic regertion modeling algorithm to classify if economic
In Progress | Medium | 2024-09-14 |  | Manual Validation | Validate classification accuracy by manually checking or comparing with existing labeled data.
Not Yet Started | Low |  |  | write methodology
Polarity Sentiment Calculation (Two Methods) |  |  |  |  | Two sets of sentiment polarity scores for each economic article
Complete | High | 2024-09-14 | 2024-09-14 | Model Analyzer 1 | Use TextBlob pre-trained machine learning model to score each article based on its overall sentiment.
In Progress | High | 2024-09-14 |  | Model Analyzer 2 | Use BERT pre-trained machine learning model to score each article based on its overall sentiment.
Not Yet Started | Medium |  |  | Sentiment Comparison | Compare results of both sentiment methods and evaluate consistency and reliability
Not Yet Started | Low |  |  | write methodology | Details of task here
Prominence Index Calculation |  |  |  |  | Define the salience index based on article's prominence in the newspaper
In Progress | Medium | 2024-09-04 |  | article prominence | Define article prominence based on advertising worth of location
In Progress | Medium | 2024-09-01 |  | article relative length | Define article relative length for each newspaper and section
Not Yet Started | Medium |  |  | Task | Details of task here
Not Yet Started | Medium |  |  | write methodology
Analysis and Reporting |  |  |  |  | Comprehensive report with findings, visualizations, and methodology
Not Yet Started | Medium |  |  | Trend Tracker | Analyze sentiment trends over time or across different newspapers
Not Yet Started | Medium |  |  | Visualization Generator | Create visualizations of sentiment distribution trends vs economic events
Not Yet Started | Medium |  |  | Reporting & Presentation | Summarize findings, methodology, and recommendations in a report or presentation format
Complete | Medium |  |  | Task | Details of task here